## Cover Page
AI Course
Capstone Project
Work Breakdown Structure
For students
ⓒ2023 SAMSUNG. All rights reserved.
Samsung Electronics Corporate Citizenship Office holds the copyright of this document.
This document is a literary property protected by copyright law so reprint and reproduction without permission are prohibited.
To use this document other than the curriculum of Samsung Innovation Campus, you must receive written consent from copyright holder.
Samsung Innovation Campus

## WBS
Capstone Project Work Breakdown Structure (WBS)
Done
In-progress
Delayed
Today |  | 2024-08-15
Project Team Name |  | AI01 - 01
Project Topic |  | Sales Consulting ChatBot
Task |  |  | Start date | End date | Responsibility | Deliverable | Task Status | W1 |  |  |  |  | W2 |  |  |  |  | W3 |  |  |  |  | W4 |  |  |  |  | W5 |  |  |  |  | W6 |  |  |  |  | W7 |  |  |  |  | W8 |  |  |  |  | W9 |  |  |  |  | W10 |  |  |  |  | W11 |  |  |  |  | W12 |  |  |  |  | W13
[8 empty] | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28 | D29 | D30 | D31 | D32 | D33 | D34 | D35 | D36 | D37 | D38 | D39 | D40 | D41 | D42 | D43 | D44 | D45 | D46 | D47 | D48 | D49 | D50 | D51 | D52 | D53 | D54 | D55 | D56 | D57 | D58 | D59 | D60 | D61 | D62 | D63 | D64 | D65
 | time axis 2024-06-11 to 2024-08-14
General Research |  |  | 2024-08-15 |  |  |  | Done | bar: 2024-06-11 to 2024-07-12
| Research ChatBot model | [5 empty] | Done | bar: 2024-06-11 to 2024-06-20; 2024-07-01 to 2024-07-12
| Collect data | [5 empty] | Done | bar: 2024-06-11 to 2024-06-20
| Build ChatBot | [5 empty] | Done | bar: 2024-06-21 to 2024-07-12
Evaluate ChatBot | [6 empty] | In-progress | bar: 2024-07-13 to 2024-07-28
| Evaluate accuracy | [5 empty] | In-progress | bar: 2024-07-14 to 2024-07-22
Upgrade code | bar: 2024-07-21 to 2024-07-28
| Find a method for auto evaluating | [5 empty] | In-progress | bar: 2024-07-14 to 2024-07-18
| Apply other data preprocessing tenichniques for bot | [5 empty] | In-progress | bar: 2024-07-13 to 2024-07-16
| Collect more data | [5 empty] | In-progress | bar: 2024-07-13 to 2024-07-20
Finish the ChatBot and report | [6 empty] | In-progress | bar: 2024-07-29 to 2024-08-14
| Collect more chat conversation data | [5 empty] | In-progress | bar: 2024-07-29 to 2024-08-02
| Check new accuracy for bot after upgrades | [5 empty] | In-progress | bar: 2024-08-02 to 2024-08-09
| Write report | [5 empty] | In-progress | bar: 2024-07-30 to 2024-08-14
| Prepare presentation | [5 empty] | In-progress | bar: 2024-07-30 to 2024-08-14
In-progress
In-progress